Republic of Macedonia

Ministry of Information Society and Administration

END OF TERM SELF ASSESSMENT REPORT

2014-2016 ACTION PLAN FOR OPEN GOVERNMENT PARTNERSHIP

Skopje, August 2016

Contents

Introduction	3

National Action Plan Process	3

Consultations during the Action Plan preparation process	4

Implementation of National Action Plan commitments	5

1.	PARTICIPATORY POLICY CREATING	5

2.	OPEN DATA	14

3.	FREEDOM OF INFORMATION	18

4.	CORRUPTION PREVENTION AND RESTRAIN AND PROMOTION OF THE GOOD GOVERNMENT PRINCIPLES	24

5.	EFFICIENT PUBLIC RESOURCE MANAGEMENT (FISCAL TRANSPARENCY)	32

6.	LOCAL LEVEL OPENNESS	37

Conclusion, other initiatives and future steps	44

# Introduction

Republic of Macedonia joined the Global Initiative for Open Government Partnership in 2011. According to the obligations all countries that joined the initiative had to submit action plans for implementing the measures from the Initiative, the Government has adopted the first Open Government Partnership Action Plan on 01.06.2012. Based on the directions and commitments, a Report on implementation of the action plan was already prepared in 2013 forming the basis for the 2014-2016 Second Open Government Partnership Action Plan with the recommendations of the independent monitoring mechanism, which was adopted by the Government on 20.05.2014.

The Second 2014-2016 Open Government Partnership Action Plan was focused on six priority commitments: participatory policy creating, open data, freedom of information, preventing corruption and promoting good governance, efficient management of public resources (fiscal transparency) and openness on local level.

Over the recent years, Republic of Macedonia has achieved results in the fields influencing the realization of the basic principles for Open Government Partnership. Large number of activities to improve the efficient operation of state institutions, increase transparency and public access to information, anti-corruption work and high quality public services to citizens and businesses by using technology and innovation powers.

# National Action Plan Process

In September 2013, by virtue of the received documents from the leading institutions of the individual measures, Ministry of Information Society and Administration has prepared a report for implementation of 2012-2014 Action Plan with prior timely conducted consultation (the portal e-democracy and direct invitation for comments sent to all ICT chambers, citizens and NGOs who took participation on previous activities regarding Open government partnership Action Plan). The preparation of 2014-2016 Open Government Partnership Action Plan was initiated in December 2013, based on the report on implementation of the 2012-2014 Action Plan, and the recommendations of the independent monitoring mechanism.

In the early stage of the process was emphasized that the preparation of the new plan needs to actively involve all parties in defining priorities according to Open Government Partnership initiative, implementation of these measures and their monitoring by the institutions, establishment of a working group with representatives nominated by the institutions that will be contact persons holders of individual measures, in order to show full coordinated approach to implement  the Open government partnership initiative measures at all institutions’ level  and the Ministry of Information society and administration continues to coordinate the process of monitoring the implementation of the action plan, submitting regular reports on an international level and ensuring wide public consultation process in accordance with the guidelines for all member countries of this global initiative. Hence, the Ministry of Information Society and Administration started the coordination process of creating a new Action Plan for 2014-2016, with nominated representatives from all institutions implementing individual measures as well as civil society representatives, according to the request and direction of the international rules of the Open government partnership Global Initiative.

# Consultations during the Action Plan preparation process

According to the established timetable, the consultation process for the drafting process of 2014-2016 Open Government Partnership Action Plan lasted two months and was conducted on the portal e-democracy where all proposals received from institutions and civil society were dully published. Meetings with institutions and civil society representatives were also held for each priority separately, as well as two public meetings where the second was in a form of workshop where each working group defined the measures on specified priorities. As a result of this broad consultation process with all relevant state bodies, with over 40 representatives from civil society associations and representatives of international organizations and embassies in the country, the second 2014-2016 Open Government Partnership Action Plan was drafted and the same was  adopted by the Government on 20.05.2014 and published on the portal e-demokrtija. Upon acceptance, the Ministry of Information Society and Administration in June 2014, submitted the Action Plan in English to the International Open Government Partnership in Washington and published the same on opengovparnetrship.org.

Consultations during the Action Plan implementation process

Working group with all relevant stakeholders regarding separate priority areas was set up for implementation of 2014-2016 Open Government Action Plan: participatory policy creating, open data, freedom of information, preventing corruption and promoting good governance, efficient management of public resources (fiscal transparency) and local level openness. Each working has a group coordinator, deputy coordinator and members (representatives of relevant institutions and civil society representatives – outside the capital of the Republic of Macedonia) that contributed to the implementation of the measures of the action plan.

The work and dynamics of meeting was responsibility of the working groups while the coordinators were responsible for preparing quarterly reports and undertaking ongoing activities on regularly held meetings of the working groups, not excluding participation by the independent monitor for Republic of Macedonia. Apart from the working meetings according to working groups by priorities, the consultation during the implementation of the action plan measures was conducted by e-mail where central point for review and comment was provided on the portal e-democracy. 5 quarterly reports on progress in implementing the 2014-2016 Open Government Partnership Action Plan were elaborated and approved by the Government in the period of June 2014 - June 2016.

IRM recommendations

Based on the challenges and findings set out in the 2012-2013 Progress Report prepared under the independent reporting mechanism, the following main recommendations were taken into account during the preparation of 2014-2016 Open Government Partnership Action Plan:

- The drafting of the Action Plan for 2014-2016 does not expand the list of priorities; the activities were directed towards defining more concrete and measurable actions that the institutions themselves have identified as key to achieving their goals.

-  in order to raise public awareness and creating a participatory environment for stakeholders, the portal e-demokrtija published timeframe for implementation of planned activities regarding preparation of the new plan and planned activities for implementation of the consultations.

- The Minister of Information Society and Administration adopted a decision to establish a working group with all stakeholders for implementation of the 2014-2016 Open Government Partnership Action Plan concerning the implementation of priority and individual measures.

# Implementation of National Action Plan commitments

Below is a tabulation of the results achieved for each priority of the 2014-2016 Action Plan.

| ## PARTICIPATORY POLICY CREATING |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  | Ministry of Information Society and Administration and General Secretariat of the Government |  |  |  |  |
| Name of responsible person from implementing agency |  | Gordana Gapikj Dimitrovska, coordinator Vesna Vasileva, deputy coordinator |  |  |  |  |
| Title, Department |  | Head of the Unit Head of the Unit |  |  |  |  |
| Email |  | gordana.dimitrovska@mioa.gov.mk Vesna.vasileva@gs.gov.mk |  |  |  |  |
| Phone |  | +389(02)3 200-944 +389(02)3 3118-022 |  |  |  |  |
| Other Actors Involved | Government | Ministry of Information Society and Administration and General Secretariat of the Government |  |  |  |  |
|  | CSO, private sector, working groups, multi-lateral groups | Macedonian Center for International Cooperation (MCIC), Center for Research and Policy Making (CRPM), Center for Change Management (CUP) ECO-AWARENESS, Institute for Community Development (CDI), IRES, - Biosvera Bitola, Bujrum – Tetovo, Center for Rural development - Kumanovo, Center for European development and integration - Bitola (CERI), Institute for economic strategies and international Affairs Ohrid, Skopje |  |  |  |  |
| Main objective |  | Affirmation and promotion of established practices for participatory policy creation supported by the government and the public sector. |  |  |  |  |
| Brief description of commitment (140 characters max) |  | Strengthening the relations between government and NGOs is a key principle of good governance and is an essential investment in the process of creating quality policies. |  |  |  |  |
| Relevance Briefly describe the way this commitment is relevant for further promotion of OGP values, access to information, civil society participation and technology and innovations for openness and accountability. (You can find detailed description of these values in the Note for directions regarding OGP Report) |  | This commitment includes 10 verifiable and quantifiable measures that allow promotion of the process of participatory policy-making. Strengthening the relations between government and NGOs is a key principle of good governance and is an essential investment in the process of creating quality policies. Through stakeholder participation, the government has access to new sources of ideas, information and resources that are important in the process of policy-making and decision making. The affirmation and promotion of established practices and procedures for policy-making supported by government and public sector are basis for improving the transparency and accountability of government before the public. Also, information technology that supports the established procedures of the policy provides greater openness, timeliness and accountability of the public sector. |  |  |  |  |
| Ambition Briefly describe the intended outcomes of commitment policy and how the same will make the Government more open or improve the Government by greater government openness. |  | One of the most important segments of transparent governance is cooperation with stakeholders in the process of policy-making, building partnership and undertaking necessary measures in order to stimulate and strengthen their participation. Consultations contribute to building mutual trust, developing the quality of democracy and strengthening the capacities of the NGO sector. By improving the portal Unique national electronic register of regulations (ENER) and optimization of the process of public consultation, publication of results on independent monitoring of government institutions’ openness in the processes of policy-making and law-drafting by the NGO, building capacity of CSOs to monitor the implementation of policies aimed to promote public private dialogue and to ensure greater participation of civil society in the process of making government policies. |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Мерка 1. Improving the portal Unique national electronic register of regulations (ENER) and optimization of the process of public consultation On 25.12.2014, based on the analysis of ENER and Report with findings and recommendations for further improvement of ENER, the new ENER was put into operation, and besides the new design, the same offers a new modern and practical modules such as: - Simple registration (reduced number of fields for data entry from 10 to 6. - the 4 types of users from public sector are fused into one type of user that holds the title public user - new systematization of regulations in accordance with the categorization used by the Official Gazette, which allows easy content browsing; -system configured period of automatic publication of comment, thus allowing greater accuracy of the dully publication of comments received from stakeholders; - A dial set-up, or clear display of date and time of consultation process end, allowing greater security for public users regarding the time period they can send in their comments; - Introduction of new link (news - Automatic publication of notice regarding the process start on law drafting, announcements for public hearings on draft laws and plans for RIA). ENER is being monitored within the frames of this project thus assessing public involvement at an early stage of drafting. Also, starting from June 2014, the section of ENER,, cooperation’ allows data display resulting from the project" Government Mirror’. One of the biggest benefits of the new ENER is its integration with multiplatform collaboration system for e-government, preventing submission of draft-laws for consideration in governmental procedure without prior publication of the same draft-law on ENER. In terms of visiting ENER, since its establishment in 2009 to its update in June 2012, the total number of visits was 25,122. During the next period ending in November 2015, it recorded an increase of 336 174 visits, ie 93%. Activities for promotion of ENER and trainings for its application are continuously carried out (published pamphlet for ENER, appearance on TV shows, held 5 trainings where 100 civil servants have been trained) |  |  |  |
| Deadline |  |  | September 2015 |  |  |  |
| Ambition |  |  | Continuous monitoring and promotion of quality of content, availability and application of this electronic solution through follow-up of the project ‘Government Mirror’ in close cooperation with ENER users (government and public) promotion. There is an ongoing preparation of an internal plan and schedule for implementing the promotional campaign for ENER aimed at several target groups (private sector, NGOs, citizens, academic community, chambers and associations.) This activity will be linked and used to implement measure 7 “greater public awareness and use of participatory policy-making through the internet portal e-democracy by the institutions, businesses, chambers, civil society and citizens”. |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 2. Strengthening the rules of operation and application of ENER Rules and conditions relating to application of the Single Electronic Register of the Republic of Macedonia (ENER) are established by already registered user or person who wants to sign in. After introducing the new ENER and its integration with multiplatform collaboration system for e-government in January 2015, the Government determined the procedure, the stages and steps for operation on ENER by government users. |  |  |  |
| Deadline |  |  | September 2015 |  |  |  |
| Ambition |  |  | / |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 3. Publication of results for application of " Government Mirror" MCIC monitors the publication practice od draft-laws on ENER and publishes regular weekly and monthly reviews and quarterly reports within the scope of the project "Government Mirror”. The main objective of the project is increased awareness and knowledge of civil society organizations and citizens to demand bigger accountability of the institutions as well as contribution to higher integrity. Weekly reviews are published at the beginning of every week and contain information on the draft-laws published on ENER in the previous week. Monthly reviews are published at the beginning of each month with data for the previous month and contain information on compliance and deviations from the minimum determined end date for public consultation for the previous month. Quarterly reports are published no later than one month after each quarter and are targeting more detailed analysis of the practice for publishing draft laws on ENER. 5 weekly reviews, two monthly and one quarterly report was drafted and published between 01.03.2016 and 31.05.2016. An example for civil society influence is the project itself “Government Mirror". The conclusions and recommendations resulting from “Government Mirror" reports are taken into account when redesigning the website of ENER, thereof improving its functionality. For example, one of the recommendations made in the 2014 “Government Mirror" report states:,, Ministries should be more efficient in the application of ENER. Ministries should regularly update the status of draft-laws so the public should know whether the published regulations are effectively open to advice or consultation, or whether the consultation period is closed and the regulation has entered into parliamentary procedure”. This recommendation is accepted with the amendments to ENER so now ENER displays the exact remaining consultation period, and when the consultation is concluded, there is a clear message that states "the time for comments has expired." The reports are available at: http://www.ogledalonavladata.mk/index.php/vesti/sledenje-na-ener/nedelen-pregled.html http://www.ogledalonavladata.mk/index.php/vesti/sledenje-na-ener/mesechen-pregled.html http://www.ogledalonavladata.mk/index.php/vesti/sledenje-na-ener/kvartalen-izvestaj.html |  |  |  |
| Deadline |  |  | 30.4.2016 with possibility of extension |  |  |  |
| Ambition |  |  | Activity extension |  |  |  |
| Additional information: This measure continues in 2016-2018 Action Plan as 1.1.3 External monitoring of the Unique Central Electronic Registry of Regulations (ENER) publicly published results and widely distributed to decision-makers |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Предмет на анализа во вториот дел се резултатите од следењето на минимумот стандарди и запазувањето на временскиот рок за консултации за објавените предлог-закони на Единствениот национален електронски регистар на прописи (ЕНЕР). Measure 4. Monitoring government institutions openness in the policy-making processes and law-drafting "Government Mirror”: public participation in the process of drafting laws" The third comprehensive annual report "Government Mirror”: public participation in the process of drafting laws" was published on June 1. The event was attended by representatives of several ministries and state institutions as well as representatives of civil society organizations. The analysis consists of two parts. The first assesses the openness of state authorities in communication with the public, in support of civil society organizations and in openness during preparation of specific draft-laws. The subject of analysis in the second part is the result from monitoring of minimum standards and meeting the time limit for consultations on the published draft-laws on the Unique Central Electronic Registry of Regulations (ENER). The report is available at http://www.mcms.org.mk/mk/za-nasata-rabota/istrazuvana-i-publikacii/istrazuvana/1780-ogledalo-na-vladata-2015-uchestvo-na-javnosta-vo-procesite-na-podgotovka-na-zakoni.html |  |  |  |
| Deadline |  |  | 30.4.2016 with possibility of extension |  |  |  |
| Ambition |  |  | There’s an ongoing preparation of a new Annual Report on monitoring government institutions openness in 2015. Its release is expected at the beginning of 2016. |  |  |  |
| Additional information: This measure continues in 2016-2018 Action Plan as 1.1.3 External monitoring of the Unique Central Electronic Registry of Regulations (ENER) publicly published results and widely distributed to decision-makers |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 5. “Capacity building of civil society organizations to monitor the implementation of policies " Center for Research and Policy making has conducted training through the LOTOS Project, for researchers from seven different civil society organizations that work locally, in terms of using the methodology of systematic monitoring of mechanisms for transparency and accountability at local level. Researchers have used this methodology to monitor the implementation of policies for good governance in 43 municipalities in Macedonia. Report on the results from this year’s monitoring was published in May 2015 and the same was presented to the representatives of municipalities and NGOs. |  |  |  |
| Deadline |  |  | December, 2016 |  |  |  |
| Ambition |  |  | Currently undertaking of planned activities |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 6. Raise awareness about benefits from Open Government Partnership: strengthening public private dialogue for creating OGP measures and building capacities for increased participation of civil society in OGP measures implementation " CRPM promotes the process of co-creation of the open government partnership action plan by organizing the civil society and facilitating debate to identify challenges, new commitments and measures for OGP. To this end, we organize 3 meetings to build coalitions holding discussions on several open government aspects. The first meeting was dedicated to transparency and accountability, the second to open data and access to information and the third was dedicated to effective public services. These events were attended by representatives from civil society and the public sector, business and academic community. More than 60 people attended the first two meetings and initial ideas and recommendations for measures collected during the workshops were delivered to the contact person for OGP and the same are part of the working material used during the conference "Open Government Partnership - a dialogue with civil society organizations on 2016-2018 National action plan". Conference "Open Government Partnership - a dialogue with civil society organizations on 2016-2018 National Action Plan" organized by MISA and Technical Assistance Project for Civil Society Organizations – TACSO was held on 23-24 March 2016. The two-day conference launched the initiative Open Government Partnership between civil society organizations and gave more detailed information on the progress, review and point of views for the independent monitoring mechanism and created a space for discussion between civil society organizations and government institutions regarding the experiences and challenges in the implementation of the second action plan. During the second day of the conference, mixed working groups prepared guidelines and recommendations for designing the next action plan. The draft-measures will be further elaborated and prioritized by government institutions. The second consultation meeting for drafting the 2016-2018 OGP Action Plan, organized by MISA and the Center for Research and Policy was held on May 11th 2016. The event was attended by 115 participants from various sectors. Six working groups finalized the second draft of the 2016-2018 OGP Action Plan and established that sustainable development goals can be realized through this Action Plan. |  |  |  |
| Deadline |  |  | December, 2016 |  |  |  |
| Ambition |  |  | Intensive activities before and during the consultations that are planned for drafting of the next OGP Action Plan (2016-2018) in order to raise public awareness of OGP initiative and at the same time include more stakeholders in creation and implementation of this plan. |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 7. Greater public awareness and aplication of participatory policy making through the internet portal e-democracy by institutions, businesses, chambers, civil society and citizens Portal for e-democracy (http://e-demokratija.mk) enables citizens simple and easily accessible way to state their opinion on the draft Government documents (policies, strategies, action plans, etc.), or be actively involved in decision making as well as present proposals to improve specific procedures. This portal solution offers content from 26 institutions, and the number of people who moderate the portal is 30. 257 documents are published on the portal and the forum allows debate on 158 subjects. In terms of visits to the portal e-democracy, since its establishment in February 2012 to June 2016, the number of visits to the portal is 5117 individual visits. Leaflet is made and the same aimed at promoting the opportunities offered by this portal solution and encourage stakeholders to increase its utilization. This portal solution represents a central point for consultation regarding the activities of the Open Government Partnership initiative. 489 representatives from government, civil society and the private sector and academic institutions were informed about the possibilities of the portal e-democracy during the wide consultative process for drafting the third 2016-2018 National Open Government Partnership Action Plan. Affirmation of the portal e-democracy is realized along with the promotion activities of ENER that are continually implemented and they represent a continuous and ongoing activity of MISA. |  |  |  |
| Deadline |  |  | June 2016 |  |  |  |
| Ambition |  |  | / |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They cover specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 8,, Establishing advisory body to promote cooperation, dialogue and encourage development of civil society composed of government, state government and civil society organizations representatives " In November 2014, the Department for Cooperation with NGOs -General Secretariat of the Government began consultations with civil society on the draft decision for establishment of Advisory body to promote cooperation, dialogue and encourage the development of civil society, electronically, through the website www.nvosorabotka.gov.mk. In January 2015, the General Secretariat, Department for Cooperation with NGOs organized consultation meetings with civil society in Bitola, Stip and Skopje. On 13th May 2016 (Friday), the General Secretariat - Department for Cooperation with NGOs organized a consultative meeting with civil society on the draft decision for establishment of Council for Cooperation between Government and civil society. On May 17, 2016, the Government of the Republic of Macedonia adopted the Decision on establishing a Council for Cooperation between the Government and civil society. After adopting the decision, the Government issued a public call for election of 13 members of the Council for Cooperation between the Government and civil society, coming from associations and foundations. |  |  |  |
| Deadline |  |  | Continuous |  |  |  |
| Ambition |  |  | Establishing Advisory body to promote cooperation, dialogue and encourage the development of civil society |  |  |  |
| Additional information: This measure continues in 2016-2018 Action Plan as 1.2.1 Establishment of an advisory body to promote cooperation, dialogue and encourage the development of civil society comprised of government, state government and civil society organizations representatives (followed by implementation of Strategy for cooperation between Government and civil society and the opinions and initiatives on this subject will affect the policies which are of great importance to civil society) |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 9 ,, Improved application of the Code of Good Practice for Civil Participation in the process of policy making " Once a year in August, the General Secretariat of the Government announces a call for civil society to contribute to the preparation of the Work Program of the Government of the Republic of Macedonia. Following the announced call, after receiving the submitted initiatives by civil society, the Department for Cooperation with NGOs forwards the same to relevant ministries. The initiatives of civil society organizations and Ministry’s responses are published on the Department’s website www.nvosorabotka.gov.mk. The Department for Cooperation with NGOs prepared a questionnaire, which was submitted to all ministries on 01.07.2015, in order to obtain information related to consistent application of the Code of Good Practice for Civil Participation in the process of policy making. The Analysis for application of the Code of Good Practice for Civil Participation in the process of policy making was drafted based on the obtained results with recommendations, and the same was considered by the Government on 25.08.2015, as part of the Information for the progress of activities related to the project "Cooperation between the Government and civil society." The information is published on the website www.nvosorabotka.gov.mk. Center for Research and Policy will prepare an analysis on the participation of the affected / interested parties in the policy making process as part of the project Advocacy for Open Government. There is an ongoing process for collecting data from institutions at central level and in the meantime there is an ongoing civil survey regarding what institutions offer and what citizens use in respect of the pillars of transparency, accountability and participation. This research will show how government policies can foster greater involvement of citizens and civil society organizations in decision-making process. |  |  |  |
| Deadline |  |  | Continuous |  |  |  |
| Ambition |  |  | Continuous monitoring of the consistent application of the Code of Good Practice for Civil Participation in the process of policy making and Analysis on participation of the affected / interested parties in the policy making process |  |  |  |
| Additional information: This measure goes in the 2016-2018 Action Plan as 1.2.2 Improved application of the Code of Good Practice for Civil Participation in the process of policy-making by increasing the number of initiatives from civil society for the annual Work program of the Government of the Republic of Macedonia |  |  |  |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 10. Implementation of measures from Strategy for Cooperation with Civil Sector (2012-2017) and timely updates on the website of the Department for Cooperation with NGOs A Report on the implemented measures and activities of the Strategy for Cooperation between Government and the Civil Sector (2012 - 2017) for 2014 and the same was reviewed by the Government on 03/10/2015 for 2015, which was considered by the Government on the 23.02.2016. The report is available on the website of the Department for Cooperation with NGOs www.nvosorabotka.gov.mk. Also, information on the progress of activities related to the project "Cooperation between the Government and civil society" is drafted for the period January-July 2015 and the same was considered by the Government on 25.08.2015. A new website www.nvosorabotka.gov.mk for the Department for Cooperation with NGOs in the General Secretariat is set up and the same is upgraded with new content (special section) with documents (laws and regulations important for the civil society organizations’ work); implementation of the Strategy for cooperation between Government and with civil society; financial support to associations and foundations; proposals by civil society; section with useful information and templates for establishing an association; part for the Commission for organizations which are of public interest; and also a database: NGOs, containing basic information regarding 150 associations and foundations in 20 sectors of activity, and it is updated by filling out a form by interested civil society organizations. During 2015, the number of employees and the capacities of the Department for Cooperation with NGOs of the General Secretariat was increased by employee participation in several trainings on team building, motivation and increased workplace productivity, for application of Law on donations and sponsorship in public activities, as well as several consultative meetings and promotional events organized by civil society organizations. |  |  |  |
| Deadline |  |  | Continuous |  |  |  |
| Ambition |  |  |  |  |  |  |
| Additional information: This measure continues in 2016-2018 Action Plan as 1.2.3 Participatory preparation of the new 2018-2022 Strategy for Cooperation between the Government and Civil Sector |  |  |  |  |  |  |

| ## OPEN DATA |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  |  |  | Ministry of Information Society and Administration |  |  |  |  |  |  |
| Name of responsible person from implementing agency |  |  |  | Filip Manevski – Coordinator Nadica Josifovska – Deputy coordinator Vladimir Radosavljevikj – Deputy coordinator |  |  |  |  |  |  |
| Title, Department |  |  |  | ICT Adviser ИКТ Adviser Junior Associate |  |  |  |  |  |  |
| Email |  |  |  | Filip.manevski@mioa.gov.mk Nadica.Josifovski@mioa.gov.mk vladimir.radosavljevik@mioa.gov.mk |  |  |  |  |  |  |
| Phone |  |  |  | +389(0)2 320-0870 +389(0)2 320-0878 |  |  |  |  |  |  |
| Other Actors Involved | Government |  |  | Ministry of Information Society and Administration Ministry of Education and Science Ministry of Internal Affairs State Statistics Office |  |  |  |  |  |  |
|  | CSO, private sector, working groups, multi-lateral groups |  |  | Institute for Democracy - Societas Civilis - Skopje Foundation for Internet and Society - Metamorphosis Reactor, monitor |  |  |  |  |  |  |
| Main objective |  |  |  | The aim is to use data from public sector in order to encourage: - Innovation and creation of new information, content and applications by combining or crossing the data; - Creating new services, job creation and social inclusion; - Increased accountability and transparency of the public sector; - Improving the quality of data from public sector; - Economic development and development of competition, and - Development of information society in Macedonia. |  |  |  |  |  |  |
| Brief description of commitment (140 characters max) |  |  |  | Data opening resulting from the work of the authorities and public sector institutions and facilitating their easy and simple access to all stakeholders guarantees the openness and accountability of the institutions to its citizens. |  |  |  |  |  |  |
| Relevance Briefly describe the way this commitment is relevant for further promotion of OGP values, access to information, civil society participation and technology and innovations for openness and accountability. (You can find detailed description of these values in the Note for directions regarding OGP Report) |  |  |  | This commitment has 7 verifiable and quantifiable measures that allow promoting the concept of open data and their application. The release of open data in the public sector not only contributes to transparency and accountability in the work of the authorities and public sector institutions, but also promotes greater public participation in the work of the institutions as well as directly contributes to the improvement of the economic situation in the country by giving opportunity for commercial use of this data. |  |  |  |  |  |  |
| Ambition Briefly describe the intended outcomes of commitment policy and how the same will make the Government more open or improve the Government by greater government openness. |  |  |  | Every new open data set allows the institutions (and thus the government) to increases its transparency and openness to the citizens. Open data provides greater inclusion of citizens in the creation of government policies and opens a window into the operation of the institutions. This creates a kind of civilian oversight of the institutions’ operation for better service for citizens they represent. Of course all of this requires accurate, timely and consistent data from institutions. Our commitment and ambition is always to enable larger number of data sets with better quality. |  |  |  |  |  |  |
| Milestone |  |  | unopened |  |  | limited |  | substantially |  | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 1. Open data from authorities and public sector institutions according to their technical abilities they create in exercising its powers which will make them available for use The Open Data Government portal www.otvorenipodatoci.gov.mk has a total of 154 data sets from 24 institutions. According to Article 5 of the Law on public sector data use, the authorities and public sector institutions are obliged to publish data they create in the exercise of its powers which will make them available for use, in accordance with their technical possibilities. However, the opening of the data sets is mainly run by requests from citizens and the private sector obtained via the Open data government portal. |  |  |  |  |  |  |  |
| Deadline |  |  | 2016 |  |  |  |  |  |  |  |
| Ambition |  |  | Ministry of Information Society and Administration will continue to cooperate with institutions in identifying and opening their data sets and actively promote the open data concept to the public. Citizens' requests for new data sets are actively monitored and the same shall be forwarded to relevant institutions. Future aim is opening data sets from institutions in computer-readable and structured format and phasing out and replacement of data sets published in a closed format (.pdf, .doc, etc.). |  |  |  |  |  |  |  |
| Additional information: Due to its nature, the activities of this measure are sustained (status limited) and the activities concerning this will continue in the next period. |  |  |  |  |  |  |  |  |  |  |
| Milestone |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 2. Establishment of technical standards for data format and manner of publication of these sets is established by the Minister of Information Society and Administration. The adopted Rulebook on minimum technical capabilities of the authorities and public sector institutions for publishing data and technical standards for data format and the manner of publishing those data sets is published on the open data portal. Several trainings related to presentation and informing the employees with the policy provisions have been held to relevant staff of the institutions to present and inform employees of the provisions of the policy. |  |  |  |  |  |  |  |  |
| End date |  | June 2014 |  |  |  |  |  |  |  |  |
| Next steps |  | / |  |  |  |  |  |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |  |  |  |  |
| Project level |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 3. Establishing Central data catalog from public sector released for use on the basis of data catalog from authorities and public sector institutions on www.otvorenipodatoci.gov.mk In compliance with Article 7 of the Law on public sector data use, the Ministry of Information Society and Administration is obliged to run a central data catalog from the public sector released for use on the basis of data catalog from authorities and public sector institutions and publish the same on the portal www.otvorenipodatoci.gov.mk. To this end, MIOA receives data catalog in electronic form from authorities and public sector institutions which are obliged to submit the data catalog they create when exercising their competences and responsibilities later published for use, including a date for the publication of data (in data sets) for their use, dynamics of their updates (daily, weekly, monthly and quarterly) and single link, or web location where the authority or public sector institution publishes the data. At the moment all published data sets on the open data portal are listed by institution thus forming kind of electronic catalog for the published data sets until now. |  |  |  |  |  |  |  |  |
| Deadline |  | 2016 |  |  |  |  |  |  |  |  |
| Ambition |  | Ministry of Information Society and Administration actively cooperates with all authorities in the preparation of individual catalogs for each institution. There is a plan for introduction of a further division and grouping of data sets published (or planned for publication) on the Open data portal based on the data type as well as the concerning industry. This is anticipated with the next update on the open data portal. |  |  |  |  |  |  |  |  |
| Additional information: Due to its nature activities of this measure are sustained (status limited) and the activities concerning this will continue in the next period. |  |  |  |  |  |  |  |  |  |  |
| Milestone |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 4. Establishing database of contact persons in the public sector authorities and institutions appointing a person in charge of technical adaptation and publication of data on their use, their publication on the authority’s website and responsibilities for accuracy of data catalog at www.otvorenipodatoci.gov.mk Working group with representatives from 11 institutions was established as part of the project for upgrade and modernization of government open data portal (www.otvorenipodatoci.gov.mk). This led to setup of the first database of contact persons in the public sector authorities and institutions for the project open data. This list is expanded with each new institution that joined the project as well as institutions that actively participated in trainings for the Law and Regulations on Open Data. Currently, the database of contact persons for open data in the public sector authorities and institutions contains all active participants in the process of identification of data sets and their publication. |  |  |  |  |  |  |  |  |
| Deadline |  | July 2015 |  |  |  |  |  |  |  |  |
| Ambition |  | / |  |  |  |  |  |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |  |  |  |  |
| Project level |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 5. Establishing option for submitting request by interested parties for new data sets for use There are more ways to submit applications from interested parties for new data sets for use. The most direct way is via open data portal, ie using the submission form for filing a request for a new data set (http://www.otvorenipodatoci.gov.mk/Templates/Pages/NewCatalogPage.aspx?page=37). Here the applicant should fill in contact information (for natural and legal entities) and a brief description of the requested data as well as the institution the applicant expects to obtain the requested data. The applicant should also provide a brief description of the reason for submitting the request (commercial or noncommercial) and a brief description of the business model, application, web service or other content that should result from the open data use. These requests are unlimited for the applicant and serve only for internal prioritization for application processing (preference is given to the requests that can result into new application or any new content). Another way for submitting a request for opening data is if the applicant directly addresses MISA or institution that holds the data. The procedure is similar to the above described thus in this case the requests are processed slower. |  |  |  |  |  |  |  |  |
| Deadline |  | July 2014 |  |  |  |  |  |  |  |  |
| Ambition |  | / |  |  |  |  |  |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |  |  |  |  |
| Project level |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 6. Establish a crossing-data platform (pilot 11 institutions) The upgrade of the open data portal allows crossing data of up to three data sets published on the portal. This functionality is built into the portal and requires no additional software solutions and licenses for its use. However, crossing data is possible only between data sets published as "database" (structured computer-readable format). |  |  |  |  |  |  |  |  |
| Deadline |  | September 2014 |  |  |  |  |  |  |  |  |
| Ambition |  | / |  |  |  |  |  |  |  |  |
| Additional Information (Description of what remains to be achieved and any risks or challenges in implementing the commitment.) / |  |  |  |  |  |  |  |  |  |  |
| Milestone |  | unopened |  |  | limited |  | substantially |  | completed |  |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  | Measure 7. Training for implementing the law on public sector data use During 2014 and 2015, a number of group trainings were held to key personnel from training institutions for implementation of the Law on public sector data use as well as the Regulation on open data technical requirements and limitations. Apart the group trainings, MISA holds regular meetings for issues related to implementation of the law on public sector data use with all institutions that require such meetings. |  |  |  |  |  |  |  |  |
| Deadline |  | July 2015 |  |  |  |  |  |  |  |  |

| ## FREEDOM OF INFORMATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  | Commission for Protection of Right to Free Access to Public Information |  |  |  |  |
| Name of responsible person from implementing agency |  | Oliver Serafimovski, Coordinator Cveta Trajkovska, Deputy Coordinator Indji Hodja, Deputy Coordinator |  |  |  |  |
| Title, Department |  | Junior Assosiate at the Secretariat of the Commission; Head of the Secretariat of the Commission; Junior Assosiate at the Secretariat of the Commission |  |  |  |  |
| Email |  | komspi@komspi.mk; oliverserafimovski@komspi.mk;cveta@komspi.mk; inxhihoxha@komspi.mk |  |  |  |  |
| Phone |  | 02/3118-038; 071/229-214; 071/232-857 и 071/229-289 |  |  |  |  |
| Other Actors Involved | Government | Ministry of Information Society and Administration; Ministry of Justice and Ministry of Finance |  |  |  |  |
|  | CSO, private sector, working groups, multi-lateral groups | Center for Civil Communications; Foundation Open Society – Macedonia and Association for Emancipation, Solidarity and Equality of Women in RM (ESE) |  |  |  |  |
| Main objective |  | Promotion and facilitation access to information |  |  |  |  |
| Brief description of commitment (140 characters max) |  | Improving access to public information, awareness of citizens and improving the Law on Free Access to Public Information is crucial for implementation of the law and the constitutional guaranteed right (Article 16 of the Constitution of RM) |  |  |  |  |
| Relevance Briefly describe the way this commitment is relevant for further promotion of OGP values, access to information, civil society participation and technology and innovations for openness and accountability. (You can find detailed description of these values in the Note for directions regarding OGP Report) |  | By implementing the commitments from Priority 3. Freedom of information will reduce the limitation of access to information, such as administrative silence as the main reason for restricting access to public information, lack of citizens regarding to information related to their guaranteed right of access to public information, holders of public information, as one of the main factors for implementation of commitments will increase transparency in operation, by publishing the information they have on their web sites and bulletin boards, thus making the documents they hold easily accessible to citizens or applicants for public information. Civil sector continuously improves the implementation of the Law on FAPI with its activities, holding trainings for citizens, NGOs and journalists, while the prepared application web solutions facilitates citizens’ submission of requests for access to public information to information holders . |  |  |  |  |
| Ambition Briefly describe the intended outcomes of commitment policy and how the same will make the Government more open or improve the Government by greater government openness. |  | Commission as holder of Priority 3. Freedom of information, but also as one of the implementers of the Law on FAPI, by implementing not only the efforts and activities of the Open Government Partnership Action Plan, but also by full implementation of the law, wants to completely implement the goals of full and open access to public information in the future held by all holders of public information in a manner accessible to the public (website, bulletin boards etc.) - Article 9 of the Law on FAPI. This will make the holders of public information more transparent in the publication of public information, open for cooperation with applicants-citizens, thus avoiding administrative silence as a reason for restricting access to public information. |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 4: Regular publication and update of the list of information holders All holders of information should publish the public information they hold on their web sites |  |  |  |
| Deadline |  |  | September 2015 - December 2016 |  |  |  |
| Ambition |  |  | On the training courses held for officers and officials for mediating public information, the Commission for Protection of Right to Free Access to Public Information continuously directs the officials how to apply the Law on FAPI, constantly suggests ways to publish and update the list of information holders have (on their websites or bulletin boards in the institutions). Holders of information should prepare banners or links on their web sites publishing all public information they hold at their disposal. |  |  |  |
| Additional information: Due to its nature activities of this measure are sustained (status limited) and the activities concerning this will continue in the next period. |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 9. Amendments to the Law on free access to public information and Measure 10. Establishing inter-ministerial working group to lay down the harmonization of the Convention of the Council of Europe on access to public documents and establish national legal terms for accession to this Convention Inter-ministerial working group was established to determine harmonization of the Convention of the Council of Europe on access to public documents and establish national legal terms for accession to this Convention as well as drafting an analysis for possible amendment to the Law on FAPI Measure 5: Availability of all public information on holders’ web sites Monitoring the websites of eighteen public institutions and assessing the availability of sixteen key documents and information concerning the operation of the covered institutions (work strategy, annual work program, budget calendar; pre-budget statement, Civil budget, budget proposal and adopted budget; proposal and adopted amendments to the budget, budget documents in open formats (xml or excel); monthly reports on budget execution; semi-annual report on the budget, budget annual accounts, audit report, data on the person appointed as mediator for public information and a list of public information) conducted by ESE, showed that most holders of public information have not published any of the monitored budget documents or have published or only some of the documents. This suggests to the very fact that the Law on FAPI provides a list of public information is not enough to achieve a higher level of pro-activity (proactive transparency) in public institutions. Therefore it is the group as information holder to find a way to publish all the information about their work on their websites. The Commission points out that the information that should be included in the list of public information is laid down in Article 10 of the Law on FAPI and a minimum of information that it will contain cannot be established. Measure 7: Increased cooperation of the Commission with citizens’ associations and foundations and municipalities in RM with MoUs According to the Action Plan for OGP, MoUs will be signed with the Foundation Open Society Macedonia, Center for Civil Communications and ESE. |  |  |  |
| Deadline |  |  | December 2016 |  |  |  |
| Ambition |  |  | Preparation of Draft Law Amending the Law on FAPI The release of public information on the holders’ web sites is a measure which will require constant work at all times. According to the Action Plan for OGP, in the future, the Commission will sign MoUs with the Foundation Open Society Macedonia, Center for Civil Communications and ESE, in order to broaden mutual cooperation. |  |  |  |
| Additional information: Measure 9. Amendments to the Law on free access to public information and Measure 10. Establishing inter-ministerial working group to lay down the harmonization of the Convention of the Council of Europe on access to public documents and establish national legal terms for accession to this Convention: Additional information: Due to its nature activities of this measure are sustained (status substantially) and the activities concerning this will continue in the next period, holder of this measure is the Ministry of Justice Measure 5: Availability of all public information on holders’ web sites: Due to its nature activities of this measure are sustained (status substantially) and the activities concerning this will continue in the next period. Measure 7: Increased cooperation of the Commission with citizens’ associations and foundations and municipalities in RM with MoUs: Availability of all public information on holders’ web sites: Due to its nature activities of this measure are sustained (status substantially) and the activities concerning this will continue in the next period. |  |  |  |  |  |  |
| Milestone |  |  | unopened | limited | substantially | completed |
| Description of results They include specific activities within the reporting period (first or second year of the Action Plan) and, where applicable, please indicate whether there was evidence that citizens apply that commitment or the commitment has effect. |  |  | Measure 1: Raising public awareness regarding the right to free access to public information by created and implemented media presentation and education campaign and Measure 2: Educating officials and responsible persons of the information holders - Held 4 training sessions for journalists and BIRN research network of journalists on Application of the right to Free access to public information in order to familiarize them with the Law on FAPI (Center for Civil Communications) -Held 8 two-day training sessions in several cities for citizens and representatives of associations of citizens attended by 188 people, held three training sessions for members of NGOs in Krushevo and Skopje, in cooperation with USAID, National Democratic Institute and the Young European Federalists on the following subjects: "The right to free access to information" and "Request for free access to information - a tool for monitoring public policies." (Foundation open society - Macedonia) -Constant publishing news relating to public institutions’ transparency and accountability http://www.esem.org.mk/index.php/najznachajni-vesti www.fiskalnatransparentnost.org.mk, training sessions of three civil society organizations (ESE) -In cooperation with OSCE Mission, the Commission visited 6 communities and held 6 training sessions for students and high school students, held training at the Faculty of Security in Skopje, the Law on Free Access to Public Information, ie the possibilities arising from the Law for public information applicants, as well as the obligations and duties arising from the Law for information holders. In cooperation with the Academy of Judges and Public Prosecutors "Pavel Shatev" and the Protection of Personal Data Directorate, the Commission held three training sessions for 24 presidents of courts, 18 prosecutors from the Public Prosecutor's Offices in the country, and 46 officers for protection of personal data and officials responding on requests for free access to public information from the courts and prosecutors from all appellate regions. Four trainings sessions are held and organized in cooperation with the OSCE Mission in Skopje. Four trainings are part of the six planned trainings according to the signed memorandum of cooperation between the Commission and OSCE Mission in Skopje in 2015, which marks the four-year continuous established fruitful cooperation between the two institutions. The first training was held in Skopje and the same was attended by officials and authorized persons from municipalities in Skopje, and the second workshop was held in Gostivar attended by officials and authorized persons from several municipalities in the western part of Macedonia. The third training session was organized in Stip and the same was attended by representatives of the administration of municipalities in the eastern part of the country. The fourth training for officers and officials mediating with public information was held in Demir Kapija. Also, according to the previously signed Memorandum of Cooperation with the Faculty of Computer Science and Engineering, trainers from the Commission held presentation to the students at the Faculty’s premises on the guaranteed right, regulated by the Law on Free Access to Public Information. Commission Representatives held lecture to executers and other representatives from different levels of the judiciary in the country on "Practical application of the Law on free access to public information in terms of execution." Three training sessions were held to about 60 officials-holders of public information, and the aim was raising public awareness and level of understanding for public information holders regarding the Law on FAPI and obligations deriving from the Law, as well as the way of exercising the right to free access to public information. Training session was held for students of the Faculty of Security after previously signed memorandum. The application solutions of Open Society Institute Macedonia (http://slobodenpristap.mk/) and ESE (http://www.fiskalnatransparentnost.org.mk/) are featured in a form of banner / link the on the website of the Commission. Citizens now have very simple and fast way to exercise the right to submit request to the holders of public information. Two training sessions were held by Expert lecturers in the Secretariat of the Commission at the Commission’s premises on the subject "Free access to public information." The training was attended by 29 newly appointed officials, as well as persons who have never had any training or have never asked for additional education, and the same are representatives from state authorities and institutions, public enterprises, health institutions, authorities of the judiciary, inspectorates, funds, offices and institutes. Representatives of the Secretariat of the Commission held a lecture as part of the Seminar "Application of the Law on Free Access to Public Information", organized by the Academy for Judges and Prosecutors "Pavel Shatev." The counseling is intended for persons who act upon requests for free access to public information from all prosecutors in the country. The lecture was attended by 20 officials. Measure 3. Designing a new web location of the Commission A new web location of the Commission has been designed in cooperation with the Ministry of Information Society and Administration, and it has been in function for the information applicants and information holders’ use. The site provides all necessary information related to the Law on FAPI and it has been enriched with new link solutions with transparent presentation of the Commission’s operation. Measure 6: Improvement of the financial and human resources of the Commission The Commission’s budget for protection of the right to free access to public information (PRFAPI) has been increased for 500.000,00 MKD in the salaries part, due to the 4 persons transfer into the Commission. Measure 8: Publication of information on the budget and program implementation of the health budgets, with a special focus to the budget and financial implementation of preventive programs of the Ministry of Health, provided through the procedure for access to public information. www.esem.org.mk - According to the Measure 8, the Ministry of Health designed an application with all necessary public information that are subject to applications for public information by the Association for Women Emancipation, Solidarity and Equality (ESE) |  |  |  |
| Deadline |  |  | December 2014 – December 2015 |  |  |  |
| Ambition |  |  | / |  |  |  |
| Additional information: As a Benefit of the conducted measures, the Law on FAPI was introduced to journalists, non-government organizations, applicants, official and responsible persons with the public information holders through conducted trainings and campaigns. Also, students of a number of faculty institutions got familiar with the Law through organized lectures. The Commissions web location provides ban/link applicative solutions of the Open Society Foundation – Macedonia. (http://slobodenpristap.mk/) and the ESE Association (http://www.fiskalnatransparentnost.org.mk/). Furthermore, a new web location of the Commission has been designed and put into function, in cooperation with the MISA, which presents the Commission’s operation in the most transparent way, through providing all necessary information related to the Law on FAPI. Financial and human resources have been improved, as well as the cooperation with the Ministry of Health and the ESE Association in respect of publishing information on the budget and financial implementation of the preventive programs of the Ministry. |  |  |  |  |  |  |

| ## CORRUPTION PREVENTION AND RESTRAIN AND PROMOTION OF THE GOOD GOVERNMENT PRINCIPLES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  | State Commission for Corruption Prevention |  |  |  |  |
| Name of responsible person from implementing agency |  | Vladimir Georgiev, Deputy Coordinator |  |  |  |  |
| Title, Department |  | State Adviser, Secretariat of the SCCP |  |  |  |  |
| Email |  | vgeorgiev@dksk.org.mk |  |  |  |  |
| Phone |  | 070 342 782 |  |  |  |  |
| Other Actors Involved | Government | State Commission for Corruption Prevention Ministry of Justice, other responsible institutions and bodies, municipalities |  |  |  |  |
|  | CO, private sector, multi-lateral and working groups | Civil organizations: Research and Policy Creating Center (CIKP), Macedonian Center for International Cooperation (MCMS), Coalition – All for fair trial , TI Macedonia, Institute for Economic Strategies and International Relations Ohrid, Institute of Democracy – Societas Civilis (IDSCS), Foundation for Internet and Society – METAMORPHOSIS, UNDP, OSCE |  |  |  |  |
| Main objective |  | - Improvement of accountability and responsibility of institutions through the public administration raising awareness for reporting illegal or inadmissibly actions. - Improvement of transparency, accountability and responsibility of the central and local level institutions - Capacity strengthening of civil organizations and their improved role in work monitoring of institutions and complete quality improvement in service delivery |  |  |  |  |
| Brief description of commitment (140 characters maximum) |  | Increased transparency and accountability of institutions, raising awareness for reporting illegal or inadmissibly actions, and strengthening the role and capacities of the public for work monitoring of institutions. |  |  |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is in the OGP Values Guidance Note.) |  | The commitment includes nine measures directed toward increased civil sector participation in work monitoring of central and local level institutions, that will contribute for strengthening of transparency, openness, accountability and integrity of the public administration. Single measures of this commitment are aimed for improving the open government partnership through establishing a sustainable and continual approach of responsibility and openness of institutions toward the non-government sector and citizens, through building mechanisms for their involvement in the corruption prevention and promotion of the good government principles. Affirmation of the ICT tools providing better interaction between the municipal bodies and citizens will also contribute to improvement of the municipalities’ transparency and accountability. |  |  |  |  |
| Ambition Briefly describe the intended results of the commitment and how it will either make government more open or improve government through more openness. |  | Measures established in this commitment, individually or as a whole, provide improvement of openness in the central and local level institutions through a thorough involvement of the public in good government policy creating, integrity and corruption risk prevention. Legal regulation of a institutional system protection for persons reporting suspicion on illegal or inadmissible actions (whistleblower protection) will encourage public administration employees and citizens to report such and similar actions. Establishment of a Register of elected and appointed persons and its publication on the SCCP’s website will allow the public to have accessible information on all elected and appointed persons by the Assembly of the RM, the Government of the RM, judicial authorities and local self-government. The innovative openness and responsibility tools (through the IT tools, responsibility, transparency and accountability index and integrity index of the municipalities) are in function to create a responsive culture of the administration and citizens’ involvement in work stimulation and assessment of the municipalities. Definition of the corruption risk assessment methodology as an upgraded concept of the institutions’ integrity is directed toward strengthening of already established public internal financial monitoring, as well as monitoring of other responsibilities of the institutions set up by the Law on Introduction of Quality Management System and a common frame for work assessment (CAF), as a contribution for the public responsibility strengthening. Capacity building of the civil organizations for institutions’ work monitoring at the central and local level is of a particular importance for carrying out thematic researches and organization of conferences and workshops. |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 1. Adopted amendments to the Law on Corruption Prevention in respect of introducing an integrity system in the public and private sectors, and introducing a systematic protection of persons reporting suspicion or information on corruption or other illegal or inadmissible action – whistleblowers. In August, the Ministry of Justice set up a working group to work on a draft version of a legal solution for introducing a systematic institutional whistleblowers protection. The first draft version of the Draft Law on Amendments and Supplements to the Law on Corruption Prevention, made in respect of introducing a systematic institutional whistleblowers protection in the public and private sectors, was submitted to the Ministry of Justice on 7th October 2015. After its harmonization by the four political parties represented in the Assembly of the Republic of Macedonia, a group of MPs submitted a Draft-Law on Whistleblowers Protection to the Assembly of the Republic of Macedonia and it was adopted on the very same day in a simplified procedure in a session held on the day of its submission. Adopted Law on Whistleblowers Protection (The Official Gazette of the Republic of Macedonia, No. 196 from 10.11.2015). The Law came into force on the eighth day after its publication in the Official Gazette of the Republic of Macedonia, with its implementation starting four months after its enforcement. The laws regulating rights and responsibilities arising from employment in the public and private sectors will be harmonized with this Law no later than three months from its entry into force. On 3rd March 2016, the Minister of justice approved the bylaws arising from the Law on Whistleblowers Protection: Regulations for protected internal reporting in public sector institutions (the Official Gazette of the Republic of Macedonia, No. 46/16) Regulations for protected external reporting (the Official Gazette of the Republic of Macedonia, No. 46/16) Regulations and guidelines for adopting internal acts for protected internal reporting in the private sector legal entity (the Official Gazette of the Republic of Macedonia, No. 46/16) Implementation of the Law on Whistleblowers Protection, and implementation of the bylaws arising from it, to start on 18th March 2016. |  |  |  |
| Deadline |  |  | October 2015 |  |  |  |
| Ambition |  |  | Harmonization of the laws regulating rights and responsibilities arising from employment in the public and private sectors with the Law on Whistleblowers Protection. Establishment of the whistleblower protection mechanism: This measure continues in the AP 2016-2018, as 4.1 “Implementation of the Law on Whistleblowers Protection and raising reporting awareness” through the following achievements: Appointment of authorized persons to receive reports from whistleblowers in institutions; organization of trainings and workshops on efficient law implementation for authorized persons who receive the whistleblowers’ reports; and strengthening of the reporting awareness |  |  |  |
| Additional information: Institutions and legal entities in the public and private sectors should be prepared for the Law on Whistleblowers Protection implementation, with necessary allocation of human and financial resources for establishing the reporting and whistleblowers protection mechanism. |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 2. Carrying out activities for raising reporting awareness of the public administration and citizens to report corruption and other illegal or inadmissible actions. In organization of the TI Macedonia, a workshop was organized in April 2015 within the project “Whistleblowers advocacy and protection, including media and civil society”. According to the IT Macedonia information, an analysis was conducted within this project of the legal framework for whistleblowers in the Republic of Macedonia and comparison analysis with the countries in the region. Billboards were installed at three locations in Skopje titled “For Whistleblowers Protection”, and also two journalistic research stories were published. The purpose for the stories publication is to raise awareness of the whistleblowers’ role and consequences they suffer for their reporting. Within the IPA2010 Twinning Project “Support for efficient corruption prevention”, the Component 1 provides preparation of publications-guides for the Law on Whistleblowers Protection implementation – reporting channels and ensuring protection. Within the regional activities provided in one of the key measures on the dimension Anticorruption of the 2020 SEU Strategy, a Coalition for whistleblowers protection in South-East Europe was formed in Belgrade in November 2015, involving non-government organizations from the Republic of Macedonia. The Coalition will function as a civil organization umbrella for building policies, advocacy and raising awareness for whistleblowers protection, as well as a network for knowledge, practice and support exchange. The Societas Civilis Democracy Institute in Skopje made an analysis of the corruption reporting systems efficacy (first of all the electronic ones). The brief document of the public policy analyzes factors limiting efficacy of these mechanisms and proposes measures for improving future efficacy. Also, there is a proposal for designing a centralized national system for electronic corruption reporting that will provide integrated statistics and insight in the report processing, besides the reporting platform. On 10th March 2016, within the Component 1 activity 1.5 of the IPA2010 Twinning Project “Support for efficient corruption prevention”, the Conference was organized on the topic: “Harmonized corruption management and prevention in private sector”, with presentation of standards and good practices of an introductory system for harmonized management, including channels for protected reporting, and explanation of the Law on Whistleblowers Protection and other bylaws arising from it. The Conference, in organization of the Ministry of Justice, SCCP and the Twinning Office, was attended by representatives of the public sector institutions, legal entities of the private sector and business community, as well as representatives of Cos. |  |  |  |
| Deadline |  |  | 2016 |  |  |  |
| Ambition |  |  | The adoption of the legal solution for introducing institutional system whistleblowers protection will be followed by activities for rising reporting awareness. Preparation of publications – guides on the Law on Whistleblowers Protection implementation - reporting channels and ensuring protection |  |  |  |
| Additional information: This measure is included in the aforementioned measure and it will be transferred in the AP 2016-2018 as 4.1 “Implementation of the Law on Whistleblowers Protection and strengthening of the reporting awareness” achievement in the part of awareness strengthening – Preparation of publications/guides for the Law on Whistleblowers Protection implementation. |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 3. Introduction of the integrity system guidelines and their further piloting in municipalities and central level institutions In November 2014, the SCCP, ALSU and UNDP organized a joint public debate on the topic of integrity, transparency and accountability at the local level, with participation of a great number of municipalities and non-government sector representatives. The purpose of this event was to present experiences and challenges in the integrity concept introduction and to discuss the role of the civil society, as well as application of the ICT tools in promotion of the local level transparency and accountability. The topic of the local level integrity, transparency and accountability, as well as the possibility for application of the ICT technologies, innovations and open data for transparency and accountability promotion, were a part of the observation of the corruption prevention world day (9th December 2014), in joint organization by the SCCP, UNDP and ALSU, and a part of the annual conference of the SCCP for realization assessment of the National Program for corruption and collision of interests prevention and repression 2011-2015, held in March 2015. As a part of the integrity concept, the SCCP in cooperation with the UNDP continued promotion in 2014 and 2015 for signing of anti-corruption policy/local level integrity policy. So far, 47 municipalities have signed the anti-corruption policy. On 7th December 2015, the SCCP in agreement with its legal competence, adopted the National Program for corruption and collision of interests prevention and repression, with the 2016-2019 Action Plan. Within the strategic objective 1. – Strengthened institutional system and legislative for corruption and collision of interests prevention, the Action Plan provides a number of activities for developing and establishing guidelines for the public sector integrity concept. |  |  |  |
| Deadline |  |  | In continuation |  |  |  |
| Ambition |  |  | According to the Action Plan of the 2016-2018 National Program, the SCCP adopted guidelines for the public sector integrity concept |  |  |  |
| Additional information This measure continue in the AP 2016-2018 as 4.3 “Promotion of integrity, transparency and accountability at the local level and progress monitoring” |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects. |  |  | Measure 4. Definition of the corruption risk assessment methodology as an upgraded integrity concept Activities are being in progress for corruption risk assessment, taking into account already established system for internal financial monitoring, as well as responsibilities of the institutions determined by the Law on Introduction of Quality Management System and a common frame for work assessment (CAF). The OSCE Mission to Skopje, in cooperation with the SCCP, in October 2014 conducted three two-day trainings for the local self-government representatives (internal auditors and/or heads of the budget and finance sectors) as contact persons in the working groups for suggesting risk detecting measures and ways for their overcoming. The trainings were realization of the two integrity concept elements: - Training and strengthening of the internal auditor function in the local self-government units - Development of strategies for corruption risks management The trainings included 35 people from 20 local self-government units with already established functional internal auditor units within the municipal administration. The covered topics were an introduction of the integrity model, elements of the risk assessment process, steps in the corruption risk assessment, definition of the processes in the local self-government units, creation of a process map, risk assessment methodology, definition of risk monitoring measures, definition of a structure and supplements to the risk management strategy. In the period 25th – 29th January 2016, according to the PARIRP recommendations for introducing corruption risk assessment, the TAIEX expert mission “Corruption risk assessment in public sector” was realized. The TAIEX expert mission was organized on demand of the Ministry of Interior (MoI), with support of the SCCP and MF. The final report with expert recommendations was submitted by the TAIEX, before the conclusion of this quarterly report |  |  |  |
| Deadline |  |  | 2016 |  |  |  |
| Ambition |  |  | Activities in continuation This measure was completed in respect of the corruption risk assessment methodology, in accordance with the Report of the TAIEX expert mission “Corruption risk assessment in public sector”, and has been well elaborated through already established system for public internal financial monitoring. |  |  |  |
| Additional information/ |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 5. Preparation of a methodology for progress monitoring of the integrity system introduction (integrity index) in the local self-government units For realization of this measure, the SCCP in cooperation with the UNDP created two index form questionnaires in November 2014. The first index consists of 45 questions to assess degree of the responsibility, transparency and accountability of the municipalities in the fields of public procurements, financial management, urban planning and civil society involvement in the decision making process. In the first phase the index was sent to 15 pilot municipalities. Logistic support and questionnaire analysis was realized by the Research and Policy Creating center, (CIKP). The second index contains 14 question groups in accordance with the integrity concept, including questions related to the openness. The integrity index was submitted to 81 municipalities. Logistic support was provided through the ALSU, CIKP and seven COs. A small number of municipalities sent their feedback, which imposes the need for additional index promotion. |  |  |  |
| Deadline |  |  | 2016 |  |  |  |
| Ambition |  |  | Additional adaptation of the indexes for responsibility, transparency, accountability and integrity and their promotion in the municipalities. |  |  |  |
| Additional information This measure continues in the AP 2016-2018 as 4.3 “Promotion of integrity, transparency and accountability at the local level and progress monitoring”, achievement: Monitoring of the responsibility, transparency and accountability at the local level through the integrity index and the index of responsibility, transparency and accountability of the municipalities. |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 7. Continual promotion of the IT tools application for social responsibility in municipalities and other institutions In 2014, the UNDP as a part of the initiative for integrity promotion at the local level and better social responsibility, designed the “Open municipality” tool for better interaction between the municipalities and citizens, as well as for promotion of transparency, openness and accountability at the local level. The tool was initially installed in 5 municipalities, and later in additional 10 municipalities. The purpose of this initiative is to allow citizens to express their views on the municipalities’ work in respect of openness, accountability and affability of the municipal administration. By expressing their opinions, citizens can influence the improvement of service quality in municipalities. The tool is based on ITC technology, and the municipalities have set a “touch screen” where citizens can answer a questionnaire and give their opinions on the municipality openness and accountability by simply touching the screen. There is a person available in the municipality to answer any possible question. These questionnaires are also available on the Internet address: http://www.moja-opstina.mk/. This tool builds on several previous initiatives for developing ICT based social responsibility tools, developed by the non-government sector and implemented in cooperation with the municipalities. For example, the “My priority” ICT tool was implemented in the Municipality of Veles by the FOCUS non-government organization. There are activities for further promotion of innovative ICT based tools that are to improve interaction between the local government and citizens. Feedback from citizens will help to improve the integrity system by taking into account citizens’ opinions and adequate response by the municipal administration in order to achieve greater openness, transparency and accountability. |  |  |  |
| Deadline |  |  | In continuation |  |  |  |
| Ambition |  |  | Continued activities This measure has been completed and the “Open municipality” tool has been installed to provide better interaction between the municipalities and citizens, and promotion of transparency, openness and accountability at the local level. |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 8. Building capacities of the civil organizations and anti-corruption practice monitoring at the local level through a research and LOTOS study Through the LOTOS project, the Center for Research and Policy Creating (CIKP) conducted a training for seven researchers from different civil organizations dealing at the local level, in respect of application of the methodology for systematic transparency and accountability mechanisms monitoring at the local level. The researchers used this methodology for monitoring good government policies implementation in 43 municipalities in Macedonia. The Report of the one-year monitoring results, as the first systematic review of the good government at the local level, was published by the CIKP in May 2015 and presented to representatives of the municipalities and non-government organizations. Link to the results: lotos.crpm.org.mk/#/ The LOTOS project was completed by the CIKP, there are no additional activities to be taken or planned in the fourth quarter. |  |  |  |
| Deadline |  |  | / |  |  |  |
| Ambition |  |  | / This measure has been completed with the LOTOS project completion and conducted study. |  |  |  |
| Additional information / |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | Measure 9. Definition of the elected and appointed persons coverage, obliged to submit a questionnaire on their property status, as well as their interest statements – preparation of a Register In June 2015, the Law was adopted with amendments and supplements to the Law on Corruption Prevention to determine jurisdiction of the SCCP for establishing and keeping a Register of elected and appointed persons. The aim of the Register is to establish a central data base of all elected and appointed persons in the Republic of Macedonia and their publication on the SCCP website. Also, the Register will allow the SCCP a systematic and continual property and interest monitoring of the elected and appointed persons. In July 2015, the SCCP approved the Data Form for elected and appointed persons and the Rules on the content, form and manner of keeping the Register of elected and appointed persons. Within the IPA2010 Twinning Project “Support for efficient corruption prevention”, Component 6, the SCCP in cooperation with experts of the Twinning Partner from Germany conducted activities for designing a software solution for the Register of elected and appointed persons. |  |  |  |
| Deadline |  |  | 2016 |  |  |  |
| Ambition |  |  | Designing an IT solution for data base of the Register and a web application for publishing data from the Register on the SCCP’s website. This measure has been completed. A software solution has been designed for the electronic Register of elected and appointed persons. Activities are being in progress for entering data on elected and appointed persons in the electronic register data base. |  |  |  |
| Additional information / |  |  |  |  |  |  |

| ## EFFICIENT PUBLIC RESOURCE MANAGEMENT (FISCAL TRANSPARENCY) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  | Ministry of Finance, Ministry of Health, Secretariat for European Affairs |  |  |  |
| Name of responsible person from implementing agency |  | Lubica Jovceska (MF), Anka Georgievska (MH), Aleksandar Danailov and Biljana Drijovska (PPB), Xheladin Llokmani (SEA), Marijana Pavlovska (ASIPI) |  |  |  |
| Title, Department |  |  |  |  |  |
| Email |  | ljubica.jovceska@finance.gov.mk, anka.georgievska@zdravstvo.gov.mk, xheladin.Llokmani@sep.gov.mk, aleksandar.danailov@bjn.gov.mk, biljana.drijovska@bjn.gov.mk, mirce.mirkoski@bjn.gov.mk, goran.bogdanovski@bjn.gov.mk, marijana.pavlovska@investinmacedonia.com, gfilkov@ccc.org.mk, dantik@esem.org.mk, bpavlovski@esem.org.mk, blagica.korovin@sep.gov.mk |  |  |  |
| Phone |  |  |  |  |  |
| Other Actors Involved | Government | All institutions (in consultation with the Public Procurement Bureau), Foreign Investment Agency |  |  |  |
|  | CO, private sector, multi-lateral and working groups | Center for Civil Communications Center for Research and Policy Creating Women Emancipation, Solidarity and Equality Association in the RM Institute of Democracy – Societas Civilis - Skopje |  |  |  |
| Main objective |  |  |  |  |  |
| Brief description of commitment (140 characters maximum) |  | Publication of open format budget documents. Publication and narrative explanation of the health programs realization. Publication of standardized information on public procurements on the contracting bodies’ websites Publication of data on foreign investments and foreign assistance to provide a greater transparency |  |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is in the OGP Values Guidance Note.) |  | It is relevant to increase transparency and accountability of the institutions in respect of spending public money, as well as transparency of received foreign assistance and provided foreign investments through approximation of budget information and information on foreign assistance and foreign investments to the general public, as well as increased transparency of public procurement procedures. |  |  |  |
| Ambition Briefly describe the intended results of the commitment and how it will either make government more open or improve government through more openness. |  | - Continual publication of open format budget documents - Continual publication and narrative explanation of the health programs realization. - Continual publication of standardized public procurement information on the contracting bodies’ websites - Continual publication of data on foreign investments and foreign assistance to provide a greater transparency |  |  |  |
| Milestone |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  | Measure 1. Conducting the open budget initiative а) In June 2015, the Ministry of Finance published the XML format of the 2015 Budget of the RM on its official website, besides the PDF format that had been at the beginning of the year. Also, for the first time, in July 2015 was published a complete form of the final 2014 Budget of the RM (besides the general, also the special part was published) and it is available in its open format. In November 2015 was published the XML format of the amendments and supplements to the 2015 Budget of the RM, and also the 2016 Budget of the RM was published in both formats. b) Activities related to the 2015 Civil Budget were initiated in the Ministry of Finance in early 2015, and they are coming to the final stage. In parallel, in early 2015 the Ministry of Finance started initial activities for the 2016 Civil Budget preparation. c) The Ministry of Health held a meeting in July with representatives of the Women Emancipation, Solidarity and Equality Association in the RM and it was agreed that the Ministry o f Health should prepare the first version of reports for each health program by the end of August. These reports will be discussed in a joint meeting planned for the first half of September 2015. So far, reports on 8 programs have been completely agreed, and redefinition of 3 program formats has been in progress, while 12 programs have not been put on a meeting agenda for discussion. Having in mind the fact that program invoices are also coming in early 2016, the March 2016 deadline for publishing reports has been prolonged. |  |  |  |
| Deadline |  | End of 2015 |  |  |  |
| Ambition |  | Ministry of Finance to publish the 2016 Civil Budget Ministry of Health to publish reports of the health programs realization. |  |  |  |
| Additional information: Measure 1a) has been continually realized in practice and there is no need for its further including in the OP, while the measures 1b) and 1c) are transferred in the AP 2016-2018. |  |  |  |  |  |
| Milestone |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  | Measure 2. Public procurements The Public Procurement Bureau held a meeting in July 2015 with the Center for Civil Communications with participation of representatives of the Commission for Protection of the Right to Free Access to Public Information, the Ministry of Finance, the City of Skopje and ELEM AD Skopje as major contracting bodies.. It was agreed in the meeting to recommend all contracting bodies to allow access to the following data on making public procurement contracts on their websites: - publication of a Public Procurement Plan, and amendments and supplements to the Plan in the current year, - publication of the advertisement – posting a link to the ad published on the PPB’s website. - publication of a communication about a concluded contract – posting a link to the communication on the PPB’s website, and - publication of a communication about a realized contract – posting the communication on the PPB’s website and an access link to it. The Public Procurement Bureau sent the recommendations to the contracting bodies, so that they can publish documents (annual plans) immediately after their preparation and make them available both to the economic operators and the general public. The Recommendation also has been posted on the Bureau’s website. |  |  |  |
| Deadline |  | End o f 2015 |  |  |  |
| Ambition |  | / |  |  |  |
| Additional information: The defined measure has been completely realized, and a new measure in the part of public procurements has been included in the AP 2016-2018 |  |  |  |  |  |
| Milestone |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  | Measure 3. Foreign assistance and foreign investments а) The Sector responsible for marketing and communications in the Agency for Foreign Investments and Export Promotion contacted in July the Women Emancipation, Solidarity and Equality Association in the RM (ESE) and the Center for Civil Communications in order to agree meeting date for defining what data on foreign investments will be published on their website. Despite the fixed date and premises for the meeting, it was not held because there was no confirmation by the Center for Civil Communications. In November, the Agency for Foreign Investments requested a list of documents from the ESE and the Center for Civil Communications to be published on the Agency’s website. The ESE submitted the following list of data and information: concluded contracts between investors in the RM (a copy of each concluded contract); information on tax reliefs for investors approved by the RM (description of the type of relief, relief period, relief value, the amount of expenses of the Budget of the RM as a result to the approved reliefs, etc.) and information on expenses of the Budget of the RM for conducting promotional activities for attracting foreign investments (kind of promotional activities, expenses for each conducted promotional activity, etc.). The list also was supported by the Center for Civil Communications. The Agency will consider all requests from the aspect of its legal competence and will initiate a meeting with the Women Emancipation, Solidarity and Equality Association in the RM (ESE) and the Center for Civil Communications. b) The Women Emancipation, Solidarity and Equality Association in the RM submitted a request to the Secretariat for European Affairs in January 2015 for publishing data related to the funds of the Ministry of Health received from the Kingdom of the Netherlands through the ORIO Program in the Central Data Base for foreign assistance to the Government of the RM (this was agreed in the working group meeting on priority 5 in January 2015). The archives of Central Data Base for foreign assistance was searched, and it was concluded that there was no a request for the project registration in the CDAD base, and therefore the SEA cannot publish any data on the CDAD website. The Secretariat for European Affairs and the the Women Emancipation, Solidarity and Equality Association in the RM held a meeting on 26rh November in accordance with the Conclusion No. 1 of the 99th Session of the Government of the RM from 25.08.2015. In the meeting were discussed possibilities for project financing from foreign assistance. Representatives of the SEA explained that the valid procedures do not allow publication of foreign assistance data in the Central Data Base without a previous request for a project registration from the implementing institution. Also, there were discussions on enlargement possibilities. Namely, the Central Data Base provides only data on projects financed from a foreign assistance received from donor countries following a concluded contract with a clause that donated funds cannot be used for paying public duties. Therefore, the Central Data Base only contains data on projects for which the implementers have submitted a Request for public duties relief. Presently, the SEA does not have a legal possibility, and there is no legal mechanism that would oblige public institutions to submit data and requests for registration of projects financed with foreign assistance. The Secretariat for European Affairs publishes Project fiches (IPA1) and all other program and action documents of the IPA2, immediately after their approval by the European Commission’s decision. In addition, links have been provided leading directly to the European Commission’s portal in order to keep the process transparency. The Ministry of Finance – CFCD according to the current regulation publishes on its website the contract register of all so far concluded contracts through the centralized system, while the DEU publishes the contract register of all concluded contracts through the DEU on its website |  |  |  |
| Deadline |  | End of 2016 |  |  |  |
| Ambition |  | The Agency for Foreign Investments and Export Promotion, according to the Conclusion No.2 of the 99th Session of the Government of the RM, held on 25.08.2015 should hold a meeting with the ESE and the Center for Civil Communications in order to define the list of documents that should be published on the Agency’s website. The SEA should consider possibilities for publishing financial and program data on all projects financed with funds received from a foreign assistance and coordinated by the SEA, on the official websites of public institutions in the RM appearing as implementers and users, and should inform the working group about it. |  |  |  |
| Additional information: The defined measures have not been realized because ne agreement was achieved between involved government institutions and civil sector organizations. The new AP 2016-2018 includes new measures related to the foreign assistance. |  |  |  |  |  |

| ## LOCAL LEVEL OPENNESS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead implementing agency |  | Ministry of Local Self-government |  |  |  |  |
| Name of responsible person from implementing agency |  | Eli Cakar |  |  |  |  |
| Title, Department |  | State Adviser for the ministry policies communication |  |  |  |  |
| Email |  | elicakar@gmail.com |  |  |  |  |
| Phone |  | 071 226 415 |  |  |  |  |
| Other Actors Involved | Government | Ministry of Information Society and Administration, Directorate for Personal Data Protection, Commission for Free Access to Public Information, Municipalities, |  |  |  |  |
|  | CO, private sector, multi-lateral and working groups | Association of the Local Self-government Units UNDP Unit for Forums Coordination Center for Research and Policy Creating Center for Civil Communications Association for Roma Community Development in the Republic of Macedonia, SUMNAL, Center for European Development and Integration - Bitola, Educational-humanitarian Organization – Shtip, Green –Power – Veles Institute for Economic Strategies and International Relations – Ohrid Institute of Democracy – Societas Civilis – Skopje METAMORPHOSIS – Internet and Society Foundation |  |  |  |  |
| Main objective |  |  |  |  |  |  |
| Brief description of commitment (140 characters maximum) |  | Strengthening of administrative capacities and development of mechanisms and innovative tools for better government, in order to provide transparency, accountability, participatory an inclusiveness at the local level. |  |  |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is in the OGP Values Guidance Note.) |  | Decentralization process in the Republic of Macedonia has been encircled with a transfer of a great number of substantial competences at the local level. Citizens realize their fundamental life and social needs in municipalities. For these reasons, it is necessary to create conditions to urge citizens to get involved in the local level decision making processes through a greater openness of the municipalities (information, communication and openness of municipalities). In the past decade the accent was put on strengthening capacities for service delivery, as well as on ensuring adequate financing resources. Based on the conducted analysis and researches in citizens’ perceptions, the 2015-2020 Program for Sustainable Local Development and Decentralization focuses on the need for urging civil participation in decision making on issues of local competence, building partnerships between the local government and civil society, and join projects implementation. 1. One of the specific objectives is the participatory government at the local level, and activities for urging this objective are establishment of instruments for urging cooperation between the LSU and the civil sector, establishment of adequate local level administrative structures for managing consultative processes, strengthening of the LSU capacities for establishing procedures for consultative process implementation. |  |  |  |  |
| Ambition Briefly describe the intended results of the commitment and how it will either make government more open or improve government through more openness. |  | 1. Definition of minimum standards for transparency at the local level, 2. Institutionalized communication between the local government and citizens with application of new innovative forms. 3. Development of new institutional forms of cooperation between the local government and citizens (Cos) 4. Introduction of procedures and new tools for implementation of the obligatory consultation process with citizens. 5. Transformation of a part of local services into e-services in order to achieve greater efficacy, transparency and accountability. 6. Strengthening of administrative and technical capacities at the local level in order to provide greater openness and accountability toward citizens. |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | 1. Development of the local level capacities for proactive communication with citizens - A selection has been made of the last 10 municipalities within the Community Forum Program. This Program covers 2/3 of municipalities in the Republic of Macedonia, or all that showed interest and answered the public appeals. Some municipalities took part in the Program for several times on their own initiative or based on fulfilled criteria. As a result of the Community Forum Program, most of the municipalities in the Republic of Macedonia, the municipal administration and the civil sector have built their capacities for the participatory process organization and implementation, following the example of the model delivered by this Program financed by the Suisse Development Agency. Within the Community Forum Program, a training for the local administration was organized this month, to present the local budget and local finances in a simple and understandable way for the citizens. The program will be completed with closing the consultation process in the 10 last selected municipalities. |  |  |  |
| Deadline |  |  | June 2016 |  |  |  |
| Ambition |  |  | Activities in respect of strengthening capacities for the consultation process organization for local self-government and civil organizations have been planned within the measures provided in the 3rd OGP Action Plan. |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | 2. Establishment of electronic platform (dashboard) with the budget delivery indicators - 1. This activity will be realized completely within the Capacity Strengthening Process in the municipal councils, a project of the UNDP, supported by the Suisse Development Agency, within the 3rd Action Plan. A software solution has been designed and analysis conducted of the citizens’ interest in information possessed by the local government, or required to be available in this way. |  |  |  |
| Deadline |  |  | June 2016 |  |  |  |
| Ambition |  |  | The measure will be completely realized within the 3rd Action Plan. |  |  |  |
| Additional information This measure continues in the AP 2016-2018 as 6.2. Establishment of new tools for improving the financial transparency and accountability of the LSUs |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | 3. Establishment of institutional forms of cooperation between the local government and citizens (Cos) for quality service delivery - Agreements are being in a concluding phase between the municipalities in the Polog and South-West plan regions for establishing two new Inclusive Development Networks, and in that way the Inclusive Development Networks will be established in 5 plan regions. The best practice has been noticed in the Vardar plan region, and as a result various manifestations for young people have been organized with support of the UNDP in the field of tourism and for persons with special needs. Lifts and access ramps have been installed in a number of municipalities for disabled persons, and a facility has been completely adapted for the needs of civil organizations in the Municipality of Veles and the Vardar plan region. |  |  |  |
| Deadline |  |  | June 2016 |  |  |  |
| Ambition |  |  | / |  |  |  |
| Additional information |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | 4. Transformation of a part of local services into e-services - A Study on the local level e-services has been conducted |  |  |  |
| Deadline |  |  | June 2016 |  |  |  |
| Ambition |  |  | - Interactive web solutions designing - Evaluation of the efficacy degree and effectiveness in respect of service preparation and delivery from the quantity and quality aspect. |  |  |  |
| Additional information This measure continues in the AP 2016-2018 as 6.8. Improvement of the local level communal services |  |  |  |  |  |  |
| Milestone |  |  | Not begun | Limited | Substantial | Completed |
| Result description Specific activities have been included within the reporting period (first or second year of the Action Plan), and where possible, state any proofs whether the citizens have implemented the commitment or whether it has any effects |  |  | 5. Participatory policy creating at the local level – creation of procedures for conducting obligatory consultation and application of innovative tools - By organizing 95 forum sessions in 59 municipalities, the municipal administration had an opportunity to conduct a wide range consultative process for determining the budget or project priorities. The Community Forums are acceptable consultation model in 57 municipalities. |  |  |  |
| Deadline |  |  | In continuation |  |  |  |
| Ambition |  |  | Creation of local level transparency standards Preparation of procedures for a consultation process implementation |  |  |  |
| Additional information This measure continues in the AP 2016-2018 as 6.3. Improvement of the institutional mechanism functioning for local level consultations |  |  |  |  |  |  |

Table 2. Summary of the realization level for each single priority of the 2014-2016 Action Plan

Of the total number of 43 measure of the Action Plan whose implementation has been in process, 23 measures are entirely completed and marked in a blue color, 10 are of a substantial and 3 of limited realization level, marked in green color, and their realization will continue in the third 2016-2018 OGP National Action Plan, while 4 measures of substantial and 3 of limited realization level whose realization has been in continuation and will continue regularly in the future period out of the OGP Action Plan.

| PRIORITY AND MEASURES | REALIZATION LEVEL |  |  |  | STATUS |
| --- | --- | --- | --- | --- | --- |
|  | Not started | Limited | Substantial | Completed |  |
| 01.М1 Advancement of the ENER portal and optimization of the public consultation process |  |  |  |  | completed |
| 01.М2 Strengthening of the ENER operation and utilization |  |  |  |  | completed |
| 01.М3 Publication of the ENER utilization results – “Government’s Mirror” |  |  |  |  | Continues in NAP 3 |
| 01.М4 Monitoring of the Government institutions’ openness in the policy creating processes and law drafting “Government’s Mirror: public involvement in the law drafting processes” |  |  |  |  | Continues in NAP 3 |
| 01.М5 Building capacities of civil organizations for policy implementation monitoring |  |  |  |  | completed |
| 01.М6 Raising awareness of the open government partnership benefits |  |  |  |  | completed |
| 01.М7 Increased public awareness of the participatory policy creating implementation through the Internet portal e-demokratija by institutions, companies, chambers, civil society and citizens |  |  |  |  | completed |
| 01.М8 Setting up a consulting body for improvement of the cooperation, dialogue and encouraging civil sector development, consisting of representatives of the Government, state administration bodies and civil organizations |  |  |  |  | Continues in NAP 3 |
| 01.М9 Advanced implementation of the Good Practices Code for the civil sector involvement in the policy creating process |  |  |  |  | Continues in NAP 3 |
| 01.М10 Implementation of the measures of the (2012-2017) Strategy for cooperation between the Government and civil sector and timely updating of the Department for cooperation with non-government organizations’ website |  |  |  |  | Continues in NAP 3 |
| 02.М1 Open data from the public sector bodies and institutions in accordance with their technical possibilities, created within their competences and made available for use |  |  |  |  | In continuation/ out of AP for OGP |
| 02.М2 Determination of the technical norms for data format and the manner of their publication is approved by the Ministry of information society and administration. |  |  |  |  | completed |
| 02.М3 Creation of a Central Catalogue of public sector data published for use based on the data catalogue of the public sector bodies and institutions on www.otvorenipodatoci.gov.mk |  |  |  |  | In continuation/ out of AP for OGP |
| 02.М4 Establishing a database of contact persons in the public sector bodies and institutions in charge of technical data adaptation and publication for further use, their publication on the body’s website, and updated data catalogue on www.otvorenipodatoci.gov.mk |  |  |  |  | completed |
| 02.М5 Establishing a possibility for application submission by stakeholder for new data sets utilization |  |  |  |  | completed |
| 02.М6 Establishing a cross data platform (11 pilot institutions) |  |  |  |  | completed |
| 02.М7 Trainings on implementation of the Law on Public Sector Data Utilization |  |  |  |  | completed |
| 03.М1 Raising public awareness of the right to free access to public information through a created and conducted media presentation and educational campaign |  |  |  |  | completed |
| 03.М2 Education of official and responsible persons in the information holder institutions |  |  |  |  | completed |
| 03.М3 Designing a new web location of the Commission |  |  |  |  | completed |
| 03.М4 Publication and updating of the holders’ lists of information on a regular basis |  |  |  |  | In continuation/ out of AP for OGP |
| 03.М5 Availability of all public information on the holder institutions’ websites |  |  |  |  | In continuation/ out of AP for OGP |
| 03.М6 Advancement of the financial and human resources of the Commission |  |  |  |  | completed |
| 03.М7 Increased cooperation of the Commission with civil associations and foundations, as well as with municipalities in the Republic of Macedonia through the Memorandum of Cooperation |  |  |  |  | In continuation/ out of AP for OGP |
| 03.М8 Publication of information on budget implementation and health programs realization, with a special focus on the budget and financial implementation of the preventive programs of the Ministry of Health, obtained through a procedure for access to public information www.esem.org.mk |  |  |  |  | completed |
| 03.М9 Amendments and supplements to the Law on Free Access to Public Information |  |  |  |  | In continuation/ out of AP for OGP |
| 03.М10 Setting up a inter-department working group for determining harmonization of the Council of Europe’s Convention for free access to documents and determining national legal conditions for accession to this Convention |  |  |  |  | In continuation/ out of AP for OGP |
| 04.М1 Drafting law amendments |  |  |  |  | completed |
| 04.М2 Conducting activities for raising awareness of the public administration and citizens as for reporting corruption and other illegal and inadmissible actions. |  |  |  |  | Continues in NAP 3 |
| 04.М3 Introducing guidelines of the integrity system and their further piloting in municipalities and central level institutions |  |  |  |  | Continues in NAP 3 |
| 04.М4 Definition of the corruption risk assessment methodology as an updated integrity concept |  |  |  |  | completed |
| 04.М5 Drafting a methodology for progress monitoring of the integrity systems introduction (integrity index) for the local self-government units |  |  |  |  | Continues in NAP 3 |
| 04.М6 Drafting a methodology for progress monitoring of the integrity systems introduction by the civil society |  |  |  |  | 2016/measure bearer CO, no activities have been taken for establishing an integrity system methodology |
| 04.М7 Continual promotion of IT tools application for social responsibility in municipalities and other institutions |  |  |  |  | completed |
| 04.М8 Building capacities of the civil organizations for anti-corruption practices monitoring at the local level through the LOTOS Study |  |  |  |  | completed |
| 04.М9 Definition o f the scope of elected and appointed persons who are obliged to submit a questionnaire of the property status and a statement of interests – drafting a Register |  |  |  |  | completed |
| 05.М1 Implementation of the open budget initiative |  |  |  |  | Continues in NAP 3 |
| 05.М2 Public procurements |  |  |  |  | End of 2015 |
| 05.М3 Foreign assistance and foreign investments |  |  |  |  | Continues with new measures in NAP 3 |
| 06.М1 Development of local level capacities for implementation of mechanisms of proactive communication with citizens |  |  |  |  | In continuation |
| 06.М2 Establishment of electronic platform (dashboard) with budget indicators and local service delivery |  |  |  |  | Continues in NAP 3 |
| 06.М3 Establishment of institutional forms of cooperation between the local government and citizens (COs) for quality service delivery |  |  |  |  | completed |
| 06.М4 Transformation of a part of local services into e-services |  |  |  |  | Continues in NAP 3 |
| 06.М5 Participatory local level policy creating |  |  |  |  | Continues in NAP 3 |

# Conclusion, other initiatives and future steps

In general, as a conclusion it is good to point out that we are quite satisfied with the way in which the measures of the 2016-2018 OGP Action Plan have been developed and implemented. The acquired experience of the first Action Plan, recommendations for independent reporting mechanism, direct contact with representatives of the civil sector and involvement of relevant government institutions ensured improvement in our operation.

The final self-assessment showed that there was a significant progress in achieving the goals set in the Action Plan. Implementation of the commitments determined in the second 2014-2016 OGP Action Plan, besides the Government, actively involved a large number of civil organizations, through an equal representation in the working groups set up for that purpose.  The Plan implementation included a large number of activities for building partnership relations with representatives of the civil and private sectors in national policy formulating and national legislative creating, as well as in strategies and initiatives creating. Besides the strategic documents implementation, interactive web portals were opened and upgraded for the consultation process facilitation, greater transparency and possibility for creating consultation forums for views and opinions exchange. This approach always produces good results and more quality legislative, and therefore it remains to be of a top priority in the forthcoming period with improvement of the process advancement mechanisms and cooperation with the civil sector. Also, a legal regulation has been introduced for protecting people reporting suspicion on illegal or inadmissible actions (whistleblowers), thus ensuring a systematic institutional protection of the whistleblowers. Further challenge remains to be improvement of the local level institutions’ openness through a complete involvement of the public in good government, integrity and corruption risk prevention policies creating.

Today, the Republic of Macedonia has legislative that guarantees access to information, and institutions publish a wide range of information on their web portals, thus providing openness to the citizens and companies. Open data have been introduced and mechanisms designed for open data prioritization in agreement with the citizens and companies’ needs. However, this remain to be the top priority of the Partnership, having in mind the fact that open data standards are to be created in the next two years, with open data licenses definition and their posting on the open data portal.

In the part of efficient public resource management, a special attention has been paid to increasing transparency and accountability of institutions in respect of spending public money, through publishing open format budget documents, publishing narrative explanation of the health programs realization and publishing standardized public procurement information on the websites of the contracting bodies. The commitments for improving fiscal transparency remains to be the focus in the forthcoming period.

Taking into account the current report preparation, the first version of the 2016-2018 OGP Action Plan was prepared in a wide consultative process, and it is based on the achievements, findings and experiences of the second Action Plan and the recommendations of the independent reporting mechanism as a continuation of the efforts for advancement of the openness, transparency, security and efficacy of the government institutions. Based on the positive practices in implementation and monitoring of the commitments in the second Action Plan, monitoring and implementation of the third Action Plan will be carried out through the established working groups system in certain priority fields, with representation of all relevant factors from the government and civil organizations.

Experiences of the so far conducted plans and achieved degree of transparency, accountability and responsibility of the public institutions toward citizens, are the basis for new commitments of the Government of the Republic of Macedonia in dealing with daily challenges, requirements and expectations of the citizens through a close cooperation and partnership with the civil organizations.